## Manual test log
Date Time | Action | Error | Performed by | Correction.
Below is the manual tests for the deveolpment site
Date | Action | Error | Tested by | comments/fix
29-1-2021 | User sign_up mailer | un defined method method name for user | Rodney | Change name to Username in mailer
29-1-2021 | User sign up mailer | mailer doesnt fire correctly on sign_up, Error 500 | Rodney | Send grid was not properly configured
30-1-2021 | User sign in from seeds file | BCrypt error invalid hash, error 500 | Rodney | seeds file was inproperly formatted to save user encrypted passwords
30-1-2021 | Location create | 500 internal server error | Rodney | Authentication JWT was not being on the location create protected route
30-1-2021 | Location Index | TypeError no implicit conversion of symbol into string | Rodney | Error was in transform_json method,required the use of self instead of the key location
30-1-2021 | Location Create | 500 server error | Rodney | Location type_id was not properly configured as a nested param.
30-1-2021 | Location Create | 500 server error | Rodney | lcation facilities was not permitted or being sent through from react
30-1-2021 | Location Create | Blank params yet location still saved | Rodney | Added validations and reconfigured the Json object sent through params
31-1-2021 | Location index | Transform_json method not returning reviews | Rodney | transform json was targeting the location object not the review object, fixed by changing self.reviews to reviews
2021-01-02 | Location Create | Forbidden attibutes error | Rodney | User_id was removed from rails locations but not on react, Bronwyn updated React form.
2021-01-02 | Location Update | 500 server error | Rodney | the update method was looking in the wrong object for the location id, changed implementation.
2021-01-02 | Location Show | nil | Rodney | Working as expected, includes reviews as well
2021-07-02 | sign in sign out | user signs out and then new user signs in and old user is present for first two renders of the app | Rodney + Bronwyn | Bug fixed in global state
2021-09-02 | User sign up sign in action | nil | Rodney | sign up works as intended fires the sign up email.
2021-09-02 | User make a location action | nil | Rodney | a new user can create a location as intended
2021-09-02 | User make a review action | nil | Rodney | User review works both with and without images
2021-09-02 | User propsed edit action | nil | Rodney | A normal user cant edit a location, alert and email firing as intended
2021-09-02 | User proposed delete action | Alert box not rendering, otherwise working as intended | Bronwyn | bug fixed and updated
2021-09-02 | Admin deltete action | alert box rendering for admin user? | Rodney | Bug fixed by bronwyn
2021-09-02 | Admin Edit action | on edit it creates new location facilities rather than updating them. | Rodney | Bug reffered to bronwyn for react state update issue
2021-09-02 | User favourites action | nil | Rodney
2021-09-02 | Non user redirect action | nil | Bronwyn | Non logged in users are redirected to the login page when attempting to view protected routes
Below is the manual tests for the production site
2021-09-02 | User sign up sign in action | nil | Rodney | sign up works as intended fires the sign up email.
2021-09-02 | User make a location action | nil | Bronwyn | a new user can create a location as intended
2021-09-02 | User make a review action | nil | Rodney | User review works both with and without images
2021-09-02 | User propsed edit action | nil | Bronwyn | A normal user cant edit a location, alert and email firing as intended
2021-09-02 | User proposed delete action | Alert box not rendering, otherwise working as intended | Bronwyn | bug fixed and updated
2021-09-02 | Admin deltete action | nil | Rodney | Behaves as expected and deletes the item
2021-09-02 | Admin Edit action | on edit it creates new location facilities rather than updating them. | Rodney | Bug reffered to bronwyn for react state update issue
2021-09-02 | User favourites action | nil | Rodney
2021-09-02 | Non user redirect action | nil | Rodney | Non logged in users are redirected to the login page when attempting to view protected routes
Below is automated test results
Testing platform | date | Test description | Result | Comments
Rspec | 27-1-2021 | Location model validations |  | Factory bot added and produces valid models
Rspec | 27-1-2021 | Favourite model validations | Success | Factory bot added and produces valid models
Rspec | 27-1-2021 | User model validations | Success | Factory bot added and produces valid models
Rspec | 27-1-2021 | Location model validations | Success | Factory bot added and produces valid models
Rspec | 27-1-2021 | Location Facilities model validations | Success | Factory bot added and produces valid models
Rspec | 27-1-2021 | Facilities model validations | Success | Factory bot added and produces valid models
Rspec | 27-1-2021 | Review model validations | Success | Factory bot added and produces valid models
Rspec | 27-1-2021 | Location Type model validations | Success | Factory bot added and produces valid models
Rspec | 27-1-2021 | Location request spec | Success | test passes using a default route testsuite i found, will alter for a more tailored test
Rspec | 2021-03-02 | Location request spec | Success | added knock authentication cnofig to location request spec, tests pass
Rspec | 2021-03-02 | User Request spec | Success | User requests paths all working as intended
Rspec | 2021-03-02 | Simple favourites test suite implemented | Success | favourites behave as intended
Cypress | 2021-06-02 | Simple e2e test suite for user signing up and logging in set up | Mostly success | the test works in the dev enviroment for rails but not test enviroment?
Cypress | 2021-06-02 | User login e2e updated | Mostly success | configured rails to seed test database with RAILS_ENV=test rake db:test:prepare db:seed but now test envirment throws cors errors
Cypress | 2021-07-02 | User login e2e updated to include logging in and creating reviews,locations,favourites. | Mostly success | again test passes but only in dev enviroment, thismight be an issue...
Cypress | 2021-07-02 | Admin user e2e added, tests all the same features as user but tests the interactiions are different | Mostly success | test passes perfectly again only in Dev
Cypress | 2021-07-02 | moved sign up tests into their own suite and cofigured user tests to use seeded user data | Mostly success | test passes perfectly again only in Dev
Rspec | 2021-08-02 | Review test suite added | Fail? | Authentication not working correctly for review requests,

## User Story log
Manual Testing Daily Progress - LOCAL | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09
As a user I want to ses a list of locations so that I can get ideas of where to go with my dog. | Not Yet | Still has bugs | Still has bugs | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Refactor needed | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to see details of each location so I can see what's there. | Not Yet | Not Yet | Still has bugs | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Refactor needed | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want a convenient way to see facilities so that I know what is available | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to see the locations visually on a map so that I can visualise their location. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able to save my favourite locations so that I can reference them later. | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able to add loctions to the app so that I can contribute to the database and feel valued. | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able to request that admin edit or delete a location so that information is up-to-date whilst protected from malicious behaviour. | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂
As an admin I want notification when a user has requested to edit or delete a location so that I am prompted when action is needed. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Refactor needed | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As an admin I want a way to edit or delete a location so that information is up-to-date. | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able rate and comment on a location so that there is more feedback and I feel like I am contributing. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able to log in so that I have a secure account with my favourites stored. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able to log out so that I have a secure account. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂
Styling | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Done 🙂
Manual Testing Daily Progress - DEPLOYED | 2021-01-26 | 2021-01-27 | 2021-01-28 | 2021-01-29 | 2021-01-30 | 2021-01-31 | 2021-02-01 | 2021-02-02 | 2021-02-03 | 2021-02-04 | 2021-02-05 | 2021-02-06 | 2021-02-07 | 2021-02-08 | 2021-02-09
As a user I want to ses a list of locations so that I can get ideas of where to go with my dog. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to see details of each location so I can see what's there. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want a convenient way to see facilities so that I know what is available | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to see the locations visually on a map so that I can visualise their location. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Still has bugs | Done 🙂
As a user I want to be able to save my favourite locations so that I can reference them later. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able to add loctions to the app so that I can contribute to the database and feel valued. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able to request that admin edit or delete a location so that information is up-to-date whilst protected from malicious behaviour. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Still has bugs | Done 🙂
As an admin I want notification when a user has requested to edit or delete a location so that I am prompted when action is needed. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Refactor needed | Refactor needed | Refactor needed | Refactor needed | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂 | Done 🙂
As an admin I want a way to edit or delete a location so that information is up-to-date. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂
As a user I want to be able rate and comment on a location so that there is more feedback and I feel like I am contributing. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂
As a user I want to be able to log in so that I have a secure account with my favourites stored. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Still has bugs | Done 🙂 | Done 🙂
As a user I want to be able to log out so that I have a secure account. | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Refactor needed | Refactor needed | Refactor needed | Still has bugs | Still has bugs | Done 🙂 | Done 🙂 | Done 🙂
Styling | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Not Yet | Still has bugs | Still has bugs | Done 🙂